## Slide 1
Quarterly Council
Performance Report
Quarter 4 – 1 April to 30 June 2024
2
3
6
16
19
20
22
Table of Contents
Executive Summary
Adelaide Hills Council Major Projects
Performance by Strategic Goal
Customer Service Standards
Capital Works Performance
Savings Strategies
Quarterly Financial Performance

## Slide 2
Strategic Goal | Performance Indicators | Annual Business Plan Strategic Initiatives
1. Executive Summary
Chart: 
| On Track | Completed | Not Started | Deferred | Behind schedule | Cancelled
Sales | 22 | 10 | 2 | 2
3 of 6 Targets met or exceeded
5 of 8 Targets met, N/A or exceeded
Chart: 
| on track | Not Started | Completed | Behind Schedule | Deferred
Sales | 6 | 3
Chart: 
| On Track | Not Started | Completed | Behind Schedule
Sales | 2
Chart: 
| On Track | Not Started | Behind Schedule | Completed
Sales | 4 | 3
Chart: 
| On Track | Not Started | Completed | Deferred | Behind Schedule
Sales | 5 | 1
Highlights
Customer Service Standards
9
Targets met or exceeded
1
Target not met
6
N/A or No Incidents reported
Capital Performance
The primary focus of this quarter has been on completing projects that were under construction, as well as commencing early planning, scoping and design works for projects due to commence in Q1 or Q2 2024-25
Built Environment
Community Wellbeing
Economy
Natural Environment
Organisation
AHC received an honourable mention at the 2024 National Awards for Local Government, for our project implementing the activities of the “Our Watch Toolkit for Local Government”. The first steps of which are organisation focused activities promoting and supporting workplace equality & respect.
The Towards Community Led Emergency Preparedness project won the LG Professionals Excellence in Emergency Management Award.
EV chargers have been installed at the Woodside office, Stirling office and Heathfield depot and are now operational. As part of this, the upgrade of main switchboard at the Stirling Office and Library was required and will provide the basic infrastructure required for any future solar and battery storage options.
The draft 2024-25 Annual Business Plan went to public consultation in May. 215 participants provided feedback via email, online survey, petition, or in person, and was officially endorsed by Council on 1 July.
The Animal Management Plan has been approved by both the Council and by the Dog and Cat Management Board
6 of 7 Targets met, N/A or exceeded
$9.9m
of infrastructure delivered
Continuing (15)
Completed (10)
Deferred (2)
Deferred (1)
Completed (3)
0 of 4 Targets met or exceeded
2 of 3 Targets met, N/A or exceeded
Cancelled (2)
Completed (2)
Continuing (6)
Continuing (5)
Continuing (4)
Completed (3)
Risk and Challenges
Volunteering continues to be lower than pre-pandemic levels and follows the national trends. We are anticipating levels to increase in the next financial year with the reopening of Fabrik Arts and Heritage Hub.
The transition to the new CRM system has meant that there are a few customer service measures that could not be produced this quarter, however will become available as the build and rollout continues into the next financial year.

## Slide 3
Kerbside bin system collection frequency change and rural FOGO trial
Council is undertaking a 12-month food organics and garden organics (FOGO) trial in collaboration with our Waste Management Partner.
Over 600 households and a small number of businesses in parts of Woodside and Lenswood will trial the new kerbside bin collection systems. This includes a new FOGO bin for rural households and a change in the collection frequency of organics bins and landfill bins, which aims to improve the food waste diversion from landfill.
Latest News
Jul 23
Delivery of the FOGO trial has continued and is on track for completion in October 2024 following which a report will be provided to Council exploring outcomes and providing recommendations for the kerbside bin services.
Commence planning & scope
= On Track
Legend:
= Completed
= Behind Schedule
2. Adelaide Hills Council Major Projects
FABRIK Development
The FABRIK Development Project involves upgrading and enhancing the former Onkaparinga Woollen Mills site at Lobethal to create an arts and heritage hub in the central Adelaide Hills.
Submit Planning Documentation for approval
Procurement phase
Obtain full Building and Development approval and award construction contract
Begin site works
Oct 21 – Dec 21
Jan 22 – Mar 22
Latest News
Works have progressed well in spite of a number of delays with the building works to be completed in August.
Further landscaping, wayfinding, installation, and establishment of the retail pavilion will occur following completion of construction. The new hub is scheduled to open in September.
Apr 22 – Jun 22
Jul 22 – Sep 22
Sep 22 – Dec 23
Construction completion
(New date Sep 2024)
Oct 23
Sep 23
Sep 23
Oct 23
Two community information sessions to be undertaken
Identify areas for trial
Initial communications and welcome pack provided to trial participants
Trial Commencement
Sep 24
Evaluate Trial Performance
Dec 24
Consider trial outcomes and make recommendation to Council
Oct 24
Prepare trial review report

## Slide 4
Electric vehicles and charging stations
Funding has been provided to enable the purchase of approximately 12 electric vehicles (EV) during 2023-24 as well as installation of the supporting charging infrastructure.
= On Track
Legend:
= Completed
= Behind Schedule
Purchase orders placed
Arrival of first Electric Vehicles
Strategic Review of Charging Infrastructure
Engage Contractor to Install Charging at Stirling
Install Charging Infrastructure at Heathfield Depot
Dec 22
Sept 23
Dec 23
Latest News
All Electric Vehicles (14 in total) have been delivered.
EV chargers have been installed at the Woodside office, Stirling office and Heathfield depot and are now operational. The project was successfully completed.
Implement activities from “Our Watch Toolkit for Local Government”
In July 2023, Council adopted an implementation plan based on the “Ourwatch Toolkit for Local Government”.
The aim of the toolkit is to prevent violence against women and their children through a range of strategies including those with an organisational focus. This is followed by work with the community to raise awareness and to undertake population based prevention activities.
Latest News
Establish an internal working group
Develop a workplace safety plan (WSP) & internal Domestic Family Violence (DEV) Policy
Oct 23
Outcomes from the Workplace Equality & Respect Employee (WER) Survey completed in April, the WER focus group conducted in May and the Workplace Gender Equality Data Analysis have informed the final recommendation report created by Our Watch Institute (OWI) received by the administration in June 2024.
We will be using the recommendations from this report to create the new Gender Equality Action plan.
AHC received an honourable mention for this project at the 2024 National Awards for Local Government
Nov 23 – Jun 24
Remaining Electric Vehicles Received
Nov 23
Sept 23
Jun 24
Finalise construction of Charging Infrastructure at Stirling
= Not Started
Jun 24
Make a statement of commitment & communicate to workforce
Sep 23
Communicate statement to community
Nov 23
Conduct an internal gender equity audit
Develop a Gender Equity Action Plan
Community collaboration on preventative initiatives
Nov 23 – Jun 25
Implement prevention initiatives with stakeholders
Stage 4 – Share & improve
2025
Nov 23 – Jun 24
Nov 23 – Jun 24
Nov 23 – Jun 25

## Slide 5
Towards Community Led Emergency Resilience Program (TCLERP)
Following on from the Community Resilience and Readiness pilot, the program has evolved to focus on community led emergency preparedness. The name of the program also changed to be Toward Community Led Emergency Resilience Program (TCLERP).
The program has several areas of focus including:
Community Engagement
Psychological and emotional emergency preparedness community education
Recovery ready halls project – emergency preparedness for select community facilities
Vegetation management project – ensuring practices are based on best fire science and within shared land owners existing capacity
Latest News
Public consultation for new Bushfire Mitigation Landscape Strategy
Revise Readiness, Recovery and Resilience content on AHC's website to align with the CFS’s 2023-24 bushfire awareness campaign
Jan 24
Jun 24
The Towards Community Led Emergency Preparedness project won the LG Professionals Excellence in Emergency Management Award.
Communities that have completed RediCommunities workshops continue to be supported by the Community Resilience Officer to realise community led preparedness intiatives.
The final report for the Recovery Ready Halls project (funded through the Black Summer Bushfire Recovery grant) was submitted, successfully acquitting the grant.
All activities funded through Wellbeing SA's partnership agreement were completed this quarter. The final report is being prepared and is due for submission in July 2024.
= On Track
Legend:
= Completed
= Behind Schedule
Jul 23 – Mar 25
Continue to support the running of the Adelaide Hills Community Action Bushfire Network (AHCABN) community network
Support psychological and emotional emergency preparedness community education
Recovery ready halls project – emergency preparedness for select community facilities
Jul 23 – Mar 25
Mar 24
Coordinate RediCommunities Workshops in 8 communities in partnership with the Australian Red Cross
Build the capacity of council's emergency management and recovery processes
Mar 25
Mar 25
The Disability Inclusive Emergency Planning (DIEP) Forum was held in April in partnership with the University of Sydney. A final report with learnings from the forum has been prepared and shared with participants, which included people with disability, carers, representatives from state government agencies and emergency, community, disability and health services. A range of forum participants also participated in a follow up tool testing day with Professor Michelle Villeneuve from the University of Sydney, designed to support organisations to improve their ability to support emergency preparedness for people with disability.
The Landscape Management Project Officer has commenced work on a fire track audit process after being successfully awarded funding through the South Australian Disaster Risk Reduction grants program. The initiative was flagged in the Bushfire Landscape Management Strategy.
The Community Resilience Team have been selected to present about their work at the Australian Disaster Resilience Conference in Sydney in September 2024.

## Slide 6
3. Performance by Strategic Goal
Highlights
Disibility Discrimination Act (DDA) Upgrades Minor - Access upgrades region wide for compliance
The DDA upgrade project at The Summit Community Centre has been completed. This project has delivered upgraded existing disability car parking that is now compliant, and has delivered a new accessible ramp, with compliant gradient and width and ramps, that links from the disability car parking to the building entrance
Cemeteries Upgrades
Kersbrook Cemetery project completed and the official opening of Martungka Natural Burial Ground was held.
Stirling Cemetery Expansion Project completed
Carbon Management Plan - Energy upgrades, Battery & Efficiency Actions
Changed LED lighting for numerous facilities.
Upgrade of main switchboard at the Stirling Office and Library to enable Electric Vehicle charging stations and possible future solar and battery storage.
New Dog and Cat Facility
New cat holding facility is now in use as well as the expanded dog facility to allow Council to hold dogs and cats while trying to re-home animals.
Council wide solution still to be developed.
RSPCA and AWL continue to be a capacity and are unable to take unowned animals for re-homing
Installation of further Electric Vehicle charging stations
Five EV charging stations have been installed at the Stirling Library along with a significant upgrade to the switchboard.
Place making and community planning
The Your Place, Your Space community connections campaign was delivered throughout June and supported by the new online Residents Guide. The communities of Woodforde, Teringie and Rostrevor were specifically targeted for the first phase and planning is underway for rollout to target communities in the new financial year.
New videos were made highlighting the benefits and unique aspects of living in the Adelaide Hills and an interactive community forum was held for Woodforde, Teringie and Rostrevor at the Summit Community Centre with over 50 attendees.
Parking and By-laws
AHC has issued 1223 parking related expiations and 9 By-law related expiations, mainly around building sites, schools and private parking areas.
Planning & Development
There have been 296 new planning and building consent applications lodged and 285 applications determined.
Four Council Assessment Panel (CAP) meetings were held to consider 9 items in total. There were 7 consents granted by the CAP.
= Continuing
Legend:
= Completed
= Cancelled
= Deferred
= Not a Strategic initiative
Risks & Challenges
Feasibility studies for future projects
No feasibility studies were conducted during the financial year, therefore the project has been marked as cancelled.
Houghton Recreation Grounds Facility Contribution
The Houghton, Hermitage, Inglewood and Paracombe Memorial Park Committee’s application to the Office for Recreation, Sport and Racing for the Houghton Hub project was unsuccessful. Staff are currently working with stakeholders to understand next steps for the project.

## Slide 7
2. Performance by Strategic Goal
Performance Indicators
= Target Met
Legend:
= Target not met
≥ Greater than or equal to
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 100 | 0 | 0
Target
100%
Inspections of footpaths in high priority zones
N/A
Chart: 
| 2021-22 | 2022-23 | 2023-24 | 2024-25
Target | 100 | 100 | 100 | 100
Result | 100 | 100
Tonnes of recycled plastic content in products purchased by Council
34 Tonnes
Chart: 
| 2021-22 | 2022-23 | 2023-24 | 2024-25
Target | 25 | 25 | 25 | 25
Result | 14 | 37.5 | 34
Chart: 
| Category 1
Series 1 | 34
Series 2 | 11
Target
25 tonne
Delivery of capital works program
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 90 | 6 | 10
96%
Target
≥ 90%
​​Capital program delivery exceed the target at EOFY for civil infrastructure projects, due to the large volume of projects completed in Q4.
Operational tasks completed within the Civil Zone Maintenance Program
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 65 | 30 | 5
50%
Target
≥ 80%
Resourcing shortfalls were overcome in Q4 as active recruitments were concluded successfully, and labour hire appointments filled any remaining gaps. Further deployment of field devices and the development of a stormwater maintenance program also contributed to this result.
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 90 | 90 | 90 | 90
Result | 96 | 76 | 58 | 96
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 80 | 80 | 80 | 80
Result | 50 | 50 | 50 | 65
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 84 | 16
Target
100%
Compliance inspections completed within 10 business days of development completion notification
84%
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 100 | 100 | 100 | 100
Result | 100 | 100 | 90 | 84
25 Development Completion notifications were received in Quarter 4 with 84% of inspections undertaken within 10 business days of receipt of notification. While 3 cases did not meet the 10 business days, the timing for the inspections were at the request of the client.
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 76 | 4 | 20
Target
≥ 80%
Compliance inspections completed within 5 business days of notification of alleged unlawful development
76%
There were 25 cases of unlawful development reported in the 6 month period from January to June 2024. 19 out of 25 inspections were completed within 5 business days of notification providing a performance result that nearly made target.
Chart: 
| Q2* | Q4 | Q2 | Q4
Target | 80 | 80 | 80 | 80
Result | 75 | 74 | 83 | 76
*Measure changed to Bi-annual in 2022-23 ABP.
Resource constraints has resulted in the next audit being scheduled to be undertaken in August 2024 and is therefore not available for this report.
Expiation Type | Volume
Parking | 1,163
Animals | 68
By-law | 3
Local Nuisance | 15
Fire & Emergency services | 95
Health | 59
Development & Building | 53
2023-24 Expiation Statistics
Other Statistics

## Slide 8
Project ID | Strategic Initiatives | Status
B1003 | New Bus Shelter Installation Program | 
B1004 | New and upgraded footpaths | 
B1007 | Recreation Trails & Cycling Routes Framework Implementation | 
B1008 | Amy Gillett Bikeway contribution (Stage 4) | 
B1009 | DDA Upgrades Minor access upgrades region wide (compliance) | 
B2008 | Local Heritage (Privately Owned) Planning and Design Code Amendment | 
B2009 | Place making and community planning | 
B3002 | Implement irrigation systems (renewal / upgrades) | 
B3003 | Investigate and Implement central irrigation control system (region wide) | 
B3004 | Prepare turf and irrigation design/management plans for key bore water use areas | 
B3005 | Carbon Management Plan - Energy upgrades, Battery & Efficiency Actions | 
B3011 | Carbon Offsets Policy | 
B3014 | Review the Corporate Carbon Management Plan | 
B4006 | Asset management - Confirm Web and Connect Licences and Field Devices | 
B4009 | Building Upgrades - minor | 
B4010 | Cemeteries Upgrades | 
B4011 | CWMS Capacity Upgrades (Birdwood & Woodside gravity mains) | 
B4014 | Road Safety Program including co-contribution to Road Blackspot | 
B4015 | Installation of further Electric Vehicle charging stations | 
B4016 | Purchase of Electric Vehicles cars for fleet | 
B4042 | Operational worksite review including forward planning | 
B4043 | Hamilton Hill - Dunfield Estate & Crest Maintenance | 
B4044 | Feasibility Studies for future projects | 
B4045 | Stormwater projects | 
B4050 | Merchants Hill retaining wall | 
B4051 | Croft Road resealing | 
B4052 | Renew the fuel monitoring and delivery system | 
B4053 | Next Step planning for Adelaide Hills War Memorial Swimming Centre, Woodside | 
B4054 | Houghton Recreation Grounds facility contribution | 
Progress on Strategic Initiatives from the Annual Business Plan
= Continuing
Legend:
= Completed
= Cancelled
= Deferred

## Slide 9
Highlights
Tour Down Under 2024
Council has approved the hosting of four stages in 2025 including:
  Women’s stage 3 (19 Jan 25) with a start and finish in Stirling
  Men’s stage 1 (21 Jan 25) with a finish in Gumeracha
  Men’s stage 3 (23 Jan 2025) with a finish in Uraidla.
Community Centres
Staff resources are being shared across community centres to ensure adequate program coverage. Community Centres are now releasing 4 programs with school holidays included, rather than 8 separate programs.
Attendance at the Torrens Valley Community Centre exercise programs have increased to a point where we have a waitlist on some classes.
Positive ageing
Despite the season, participation in social support group programs has remained strong. Many clients are focused on maintaining their strength through regular fitness classes and are enthusiastic about the special program outings.
Provided 1,700 hours of support in and around the home, over 5,000 hours of social support group activities in the community, and nearly 700 transport trips.
Fabrik – Arts & Heritage hub
Council endorsed Fabrik's Business and Implementation Plan which was presented to Council in May.
Climate Change Adaption Plan Projects-All hazards emergency management
Review of the risk assessments using a summarised version of the National Emergency Risk Assessment Guidelines has been completed.
Cultural Development
Sculpture Shelter installed at Lewis Yarlupurka O'Brien Reserve in Hamilton Hill
National Reconciliation Week screening of The last Daughter
Native foods and CulturalArt workshops for NAIDOC were held
Participants for the Public Art Mentorship "elevate+ create“ with artist Wendy Dixon-Wylie and in partnership with Oakbank School has been recruited
Volunteering
To celebrate National Volunteer Week 2024, over 660 community volunteers attended a free movie provided by AHC, MBDC and Alexandrina Council at three locations: Lobethal Cinema, Wallis Cinema in Mount Barker, and Victa Cinema in Victor Harbor. Feedback was extremely positive and volunteers who attended enjoyed the celebrations
Public Health
Undertook 67 food premises inspections, 53 were scheduled inspections with 9 follow inspections, 3 pre-opening inspection and 1 complaint inspection.
64 new wastewater applications were submitted of which 39 have been approved. 117 inspections in relation to wastewater applications were also undertaken.
33 health related complaints have been reviewed
= Continuing
Legend:
= Completed
= Cancelled
= Deferred
= Not a Strategic initiative

## Slide 10
Performance Indicators
= Target Met
Legend:
= Target not met
≥ Greater than or equal to
Feedback from Community Centre Participants
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 80 | 3 | 17
Target
85%
80%
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 80 | 0 | 20
Target
80%
78%
Feel better connected to other in the community
Will use the knowledge/skills gained in the future
242 of 303 surveyed felt they agreed or strongly agreed that they felt better connected to others and the community due to their involvement in the community centres.
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 67 | 3 | 30
6.7
Target
≥ 7
Positive ageing wellbeing score
Average level of self-determined wellbeing of program participants reviewed in the quarter.
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 7 | 7 | 7 | 7
Result | 7.1 | 7 | 7.2 | 6.7
The overall wellbeing score has dipped to 6.7 in the fourth quarter of the 23-24 year.
Many clients are struggling due to seasonal reasons as well as personal hardships/situations and illness. The quotes from people with lower scores discussed physical limitations and illness.
Number of volunteer hours contributed to AHC programs each year
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 3530 | 1270 | 1500
Target
≥ 4,800 per quarter
2937
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 4800 | 4800 | 4800 | 4800
Result | 3530 | 3183 | 2893 | 2937
A total of 2937 volunteer hours have been recorded for this quarter, slightly up from last quarter. This follows the National and International trend.
Active volunteer recruitment continues and as Fabrik Programs commence the volunteer hours should increase.
219 of 283 surveyed felt they agreed or strongly agreed they had gained new knowledge and skills due to their involvement in the community centres.
Project ID | Strategic Initiatives | Status
C4006 | Play Space Framework Implementation | 
C4012 | Climate Change Adaption Plan Projects-All hazards emergency management | 
C4021 | Community & recreation facilities framework implementation | 
C4022 | Towards Community Led Resilence Program | 
C4024 | Implement activities from "Our Watch Toolkit for Local Government" | 
C5003 | Actions from adoption of Aboriginal Place naming Action plan | 
C6001 | Fabrik Activation Capital | 
C6003 | Capital Divestment - Capital Cost | 
C6006 | Tour Down Under 2024 | 
Progress on Strategic Initiatives from the Annual Business Plan
= Continuing
Legend:
= Completed
= Cancelled
= Deferred

## Slide 11
Highlights
Review and upgrade Council corporate signage and branding
Council roadside and wayfinding signage has been updated at Stirling, Woodside, Gumeracha service centres and The Summit Community Centre.
Performance Indicators
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 100 | 0 | 0
Target
≥ 85%
Percentage of new development application decisions upheld in Council/CAPs favour under appeal
One new Appeal against a CAP Decision was lodged in Quarter 4, increasing the total planning appeals to three (3). One Appeal was resolved through approval of a compromise proposal by CAP and the matter did not progress to a hearing. The OTR appeal in the ERD Court still continues with a compromise proposal not supported by CAP. The two remaining appeals will continue into the 2024/25 FY.
nil
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 85 | 85 | 85 | 85
Result | 0
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 85 | 5.1 | 9.9
Target
≥ 85%
Percentage of planning consents completed within statutory timeframes
​​​In Quarter 4 Council issued 198 Planning Decisions with an average assessment time of 24.72 business days. Overall 87.37% of Planning Decisions were issued within statutory timeframes in Quarter 4.
87.3%
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 85 | 85 | 85 | 85
Result | 95 | 95.8 | 90.1 | 87.3
Average number of days for building consents
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 8.9 | 11.1 | 10
Target ≤
20 Business
Days
6.8
In Quarter 4 Council issued 87 Building Decisions with an average assessment time of 6.82 days. Overall 94.25% of Building Consents were issued within statutory timeframes in Quarter 4.
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 20 | 20 | 20 | 20
Result | 12 | 13.7 | 8.9 | 6.8
= Target Met or N/A
Legend:
= Target not met
= N /A – cant be assessed
≥ Greater than or equal ≤ Less than or equal
Project ID | Strategic Initiatives | Status
E2001 | Review and upgrade Council corporate signage and branding | 
E4001 | Additional Tree safety work required to support the Tour Down under | 
Progress on Strategic Initiatives from the Annual Business Plan
= Continuing
Legend:
= Completed
= Cancelled
= Deferred
= Not a Strategic initiative

## Slide 12
Resilient community facilities and open space including water fountains
Shelters have been installed in the newly upgraded playspaces - Protea Reserve and Sherry Park
Fire Prevention
Council inspection over 19,000 properties and issued 199 105F notices.
As fire danger season is now over, Council has received over 240 CRM requests for burning permits since 1 May 2024
Animal Management
Animal Management Plan has been approved by both the Council and by the Dog and Cat Management Board
Highlights
Post prescribed burn weed management
Weed control undertaken by contractors at all 10 treated sites.
10 new proposed sites have now been endorsed by Council Members.
Open Space Biodiversity
Provided 20 Butterfly kits giveaways totaling 300 additional plants being planted in region
Secured two $10,000 heritage agreement grants for Woorabinda and Lobethal.
Successfully won a $20,000 Grassroots Grant for "Improving habitat quality at Mylor Parklands for Osborn's Eyebright" project
Secured a $7,500 contribution from Hills and Fleurieu Landscape Board for Erica Control at Mylor.
Grassroots grant for "Riparian restoration or Cox Creek in Bridgewater Recreation Reserve" project complete.
= Continuing
Legend:
= Completed
= Cancelled
= Deferred
= Not a Strategic initiative
Project ID | Strategic Initiatives | Status
N1007 | Develop a strategy for the management of Council trees across the district | 
N2008 | Develop informative and attractive signage in Council reserves/playgrounds | 
N2010 | Post prescribed burn weed management | 
N2011 | New Dog and Cat facility | 
N3001 | Local Climate Adaptations for landscape conservation | 
N3002 | Resilient community facilities and open space including water fountains | 
N4002 | Kerbside bin system collection frequency change and rural FOGO trial | 
Progress on Strategic Initiatives from the Annual Business Plan

## Slide 13
Performance Indicators
= Target Met
Legend:
= Target not met
≥ Greater than or equal ≤ Less than or equal
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 55 | 5 | 20
55
Annual Target
≥ 60 NVMS
& 5 reserves
Number of Blue Marker sites (NVMS) monitored using the BushRAT methodology
(actual versus planned)
71 BushRAT assessments undertaken across 55 NVMS sites and 5 reserves.
Weather impacts affected planning and final results.
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 31 | 10
31
Annual Target
≥ 31 sites
Weed Control in biodiversity sites - no. of sites complete (actual versus planned)
All 31 planned weed control program sites completed
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 90 | 7 | 3
99%
Annual Target
≥ 90%
Percentage of private properties inspected prior to bushfire season that comply with fuel load management requirements
Council Fire Prevention Officers inspected 19,596 properties of those properties 211 were found to not be compliant
Percentage change in tonnes of waste disposed to landfill compared to previous financial year
Target = increase in diversion rate (ie: reduce waste to landfill)
Percentage of nuisance and litter queries resolved
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 90 | 5 | 5
95%
Target
≥ 90%
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 90 | 90 | 90 | 90
Result | 83 | 85.5 | 92.6 | 95
Unresolved CRMs relate to Health (4), Open Space/Civil (10) and Development compliance (1).
Tonnes of green organics collected on Green organics days
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 150 | 0 | 50
551
Target
≥ 150 per quarter
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 150 | 150 | 150 | 150
Result | 180 | 481 | 235 | 551
Chart: 
| 2022-23 | 2023-24
Series 1 | 52.6 | 53.1
Number of community education actions delivered – actioned vs planned
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 15 | 0 | 1
15
Annual Target ≥ 6
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 6 | 6 | 6 | 6
Result | 3 | 6 | 10
Five education events have been held, including Give a Sheet drop off, attending Birdwood Farm Day with education stall and a bus tour of recycling facilities.

## Slide 14
Highlights
Representation review
CL Rowe and Associates have been appointed to conduct the representation review anticipated to commence in August.
Building & swimming pool compliance inspections
88 inspections of new developments have been undertaken. Of the 88 inspections, 19 were inspections of swimming pools.
Corporate Planning and Performance
The draft 2024-25 Annual Business Plan went to public consultation in May. 215 participants provided feedback via email, online survey, petition, or in person at one of the four information sessions held in:
  Woodside on 30 May
  Stirling on 4 June
  Gumeracha on 5 June
  Norton Summit on 6 June
The draft was endorsed for publication at a special council meeting on 1 July 2024
Communications, engagements and events
Council grew its social media community by 15% in 2023-24 and updated our digital e-newsletters to seamlessly integrate with our website content.
Council supported 216 community events throughout the year and delivered two major Council run events: the Santos Tour Down Under (across 3 days) and Discover, Play, Bikeway.
A new suite of internal template for staff have been developed in Canva, Facebook, Instagram, Microsoft Word and Powerpoint to provide staff with a newly branded set of resources for presentations, documents and creative assets.
Governance
Elected members commenced their mid-term mandatory training
Risks and Challenges
Diversified income study
At this stage there has been limited opportunities to explore this in more detail. This has been marked as deferred and to be considered in the development of the strategic plan.
= Continuing
Legend:
= Completed
= Cancelled
= Deferred
= Not a Strategic initiative
Project ID | Strategic Initiatives | Status
O1005 | GPS for operational vehicles | 
O3002 | Diversified income study | 
O4005 | Representation review | 
O5005 | Resource to manage building & swimming pool compliance inspections | 
O5006 | Strategic Plan Development | 
O5007 | Customer Relationship Management (CRM) system upgrade | 
Progress on Strategic Initiatives from the Annual Business Plan

## Slide 15
Performance Indicators
Number of lost time injuries
3
Annual Target
Actual
0
Decisions (Council resolutions) considered in open Ordinary and Special Council meetings during the period
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 89 | 8 | 3
Target ≥ 90%
89.4%
Council member attendance at ordinary and special meetings for the period
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 82 | 0 | 18
Target ≥ 90%
80.2%
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 90 | 90 | 90 | 90
Result | 94.7 | 81.9 | 83.3 | 89.4
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 90 | 90 | 90 | 90
Result | 81.3 | 83.7 | 74.7 | 80.2
Freedom of Information (FOI) requests received, in progress and completed within the legislated timeframe
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 75 | 0 | 25
Target 100%
100%
Freedom of Information (FOI) External reviews upholding Council’s decisions
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 100 | 0 | 0
Target 100%
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 100 | 100 | 100 | 100
Result | 100 | 75 | 100 | 100
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 100 | 100 | 100 | 100
Result | 100 | 100 | 100 | 100
​
13 Freedom of Information application received. 8 Completed within legislative timeframes with 5 carried forward in accordance with legislative requirements.
100%
During the quarter there were 18 apologies for meetings including leaves of absence.
Employee Turnover
Annual Target
7-15%
21.7%
Actual
21.7% is higher than annual target but below the national average, which at the end of March 2024 was 23% in the public sector and 13% in the private sector*.
= Target Met or N/A
Legend:
= Target not met
= N /A – cant be assessed
≥ Greater than or equal ≤ Less than or equal
Of the 132 decisions resolved by Council, 12 were confidential decisions
Overall Customer Satisfaction
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 71 | 4 | 25
Target ≥75%
N/A
Surveys are currently unavailable due to the upgrade of the CRM system. Surveys will be reintroduced in the next financial year as part of the advanced build that will incorporate automated surveys.
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 50 | 50 | 45 | 10 | 45
Customer Net Ease Score
Surveys are currently unavailable due to the upgrade of the CRM system. Surveys will be reintroduced in the next financial year as part of the advanced build that will incorporate automated surveys.
Target 50%
100%
0%
-50%
-100%
N/A
During the year there have been 3 minor injuries, eg: lacerations or muscle strains, resulting in time off work
*Data source: Australian HR institute quarterly Australian Work outlook (May 2024)

## Slide 16
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 83 | 17
4. Customer service standards
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 50 | 50
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 67 | 33
N/A
Target
≥ 75%
5.1 General Customer Standards
Answering Incoming Phone Calls
Contact centre calls answered within 30 sec
Volume of calls = N/A
Trend over time
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 97 | 3
96%
Target
≥ 80%
Updating Customer Details
Details updated
within 5 days
Volume of updates = 25
Trend over time
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 100
100%
Target
≥ 80%
5.2 Service Specific Standards – Time Based Indicators
New Event Applications
Acknowledgement of receipt within 5 days
Volume of applications = 10
Trend over time
Illegal Burning Complaints
Investigated within
24 hours
Volume of complaints = 6
Trend over time
100%
Target
≥ 80%
Health Complaints
Investigated within
24 hours
Volume of complaints = 1
Trend over time
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 99 | 1
99%
Target
≥ 80%
Illegally Dumped Rubbish
Rubbish removed
within 3 days
Volume of reports = 89
Trend over time
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 75 | 75 | 75 | 75
Result | 57 | 64
Volume | 9433 | 5043
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 80 | 80 | 80 | 80
Result | 97 | 97 | 86 | 96
Volume | 105 | 105 | 79 | 25
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 80 | 80 | 80 | 80
Result | 96 | 100 | 26 | 100
Volume | 25 | 7 | 25 | 10
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 80 | 80 | 80 | 80
Result | 82 | 100 | 83
Volume | 11 | 12 | 0 | 6
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 80 | 80 | 80 | 80
Result | 0 | 100 | 2 | 100
Volume | 1 | 1 | 2 | 1
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 80 | 80 | 80 | 80
Result | 100 | 100 | 100 | 99
Volume | 50 | 82 | 89 | 89
Results for this quarter are not available. New phone system implemented in November and new reporting process currently being implemented.
≥ Greater than or equal to
Target
≥ 80%
83%

## Slide 17
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 70 | 30
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 98 | 2
Library Services
Response to requests to purchase materials within 10 days
Volume of requests = 40
Trend over time
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 80 | 20
100%
Target
≥ 80%
Dog Attacks
Response within
24 hours
Volume of attack reports = 2
Trend over time
N/A
Target
≥ 80%
Wasps
Investigate and action within 7 days
Volume of reports = 0
Trend over time
Development Applications
Approval of fast
track planning
applications within
5 business days
Volume of applications = 4
Trend over time
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 80 | 20 | 0
Target
≥ 80%
Missed Bins
Missed bins collected within 2 days
Volume of requests = 0
Trend over time
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 92 | 8
92%
Target
≥ 80%
Request for Bin Repair or Replacement
Requests actioned within 7 days
Volume of requests = 402
Trend over time
Footpath Repairs - Hazardous
Responded and made safe within 24 hours
Volume of repairs = 0
Trend over time
Road Repairs - Hazardous
Responded and made safe within 24 hours
Volume of repairs = 0
Trend over time
70%
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 100
100%
Target
≥ 80%
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 80 | 20 | 0
Target
≥ 80%
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 100 | 0
Target
≥ 80%
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 80 | 80 | 80 | 80
Result | 66 | 46 | 76 | 70
Volume | 67 | 90 | 55 | 40
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 80 | 80 | 80 | 80
Result | 100 | 100 | 100 | 100
Volume | 11 | 11 | 6 | 2
Chart: 
| Q3 | Q4 | Q1 | Q2
Target | 80 | 80 | 80 | 80
Result | 100 | 98
Volume | 24 | 227 | 0 | 0
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 80 | 80 | 80 | 80
Result | 100 | 83 | 100
Volume | 5 | 6 | 4
Chart: 
| Q3 | Q4 | Q1 | Q2
Target | 80 | 80 | 80 | 80
Result
Volume | 0 | 0 | 0 | 0
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 80 | 80 | 80 | 80
Result | 93 | 93 | 98 | 92
Volume | 550 | 1665 | 526 | 402
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 80 | 80 | 80 | 80
Result | 100 | 100
Volume | 1 | 0 | 1 | 0
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 80 | 80 | 80 | 80
Result
Volume | 0 | 1 | 0 | 0
No
Incidents
Target
≥ 80%
No
Incidents
All requests were responded to within 10 days
No
Incidents
This is an adjusted measure for 2023-24 based on deemed to satisfy development applications only to better align with the PDI Act categories and timeframes.
≥ Greater than or equal to
Case was deemed low risk within 24 hours, case was
Resolved within 48 hours
Council no longer deals with wasps on private property

## Slide 18
Chart: 
| 1st Qtr | 2nd Qtr | 3rd
Sales | 7.7 | 4.3 | 8
Stormwater Repairs - Hazardous
Responded and made safe within 24 hours
Volume of reports = 0
Trend over time
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 98 | 2
Target
≥ 80%
Trees - Hazardous
Responded and made safe within 24 hours
Volume of reports = 42
Trend over time
Target
Less than
12 week
Development Applications
Average consent time from date of receipt
Volume of planning consents = 198
Trend over time
Low Risk Infrastructure Requests – Average Time to Resolve
Volume of Requests = 714
Trend over time
Chart: 
| Q1 | Q2 | Q3 | Q4
Volume | 889 | 745 | 786 | 596
Low Risk Infrastructure Requests – Number of New Requests
Volume of new requests = 786
Trend over time
Overall Volume of Requests
Chart: 
| Q3 21/22 | Q4 21/22 | Q1 22/23 | Q2 22/23 | Q3 22/23 | Q4 22/23 | Q1 23/24 | Q2 23/24 | Q3 23/24 | Q4 23/24
Volume | 1755 | 1741 | 1774 | 1965 | 1772 | 2033 | 3087 | 1824 | 1772 | 1553
Trend in volume of requests/customer cases for which there is an adopted service standard, excluding the volume of phone calls
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 80 | 20 | 0
Target
≥ 80%
No
Incidents
5.3 Service Specific Standards – Other Indicators
Median Consent Time 7 weeks
Resolution time of requests
Average = 180 days
Median = 24 days
80th Percentile = 324 days
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 80 | 80 | 80 | 80
Result
Volume | 0 | 0 | 0 | 0
100%
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 80 | 80 | 80 | 80
Result | 100 | 98 | 99 | 100
Volume | 48 | 48 | 76 | 42
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 12 | 12 | 12 | 12
Average | 10.84 | 12 | 12.83 | 12.72
Median | 6.9 | 6.9 | 6.2 | 6.8
Volume | 204 | 192 | 188 | 198
Chart: 
| Q1 | Q2 | Q3 | Q4
Average | 34 | 114 | 91 | 180
Median | 5.9 | 13.9 | 15.1 | 24
80th % | 24.88 | 119.87 | 132.92 | 324.95
Volume | 714 | 714 | 714 | 714
Results are using applications in the state-wide portal
≥ Greater than or equal to
6.8

## Slide 19
5. Capital Works Program
Financial Performance by Asset Category (preliminary numbers)
Highlights
Quarter 4 of 2023-24 FY represents the finalisation of the 2023-24 Capital Works Program, with approximately $9.9M of infrastructure delivered during this period.
The primary focus of this quarter has been on completing projects that were under construction, as well as commencing early planning, scoping and design works for projects due to commence in Q1 or Q2 2024-25
Commenced work on Amy Gillett stage 4, including clearing the corridor of vegetation and delivering drainage upgrades.
Delivered a new footpath for Glover St, Kersbrook, connecting the main street with the oval recreation space.
Upgraded the play space at Sherry Park, Mylor, to include a ninja course complete with ‘stopwatch’.
What’s Next
Complete the development of the Fabrik arts and heritage hub.
Finalise projects that are in progress as of 30 June.
Commence work son the 2024/25 capital works program.
Asset Category | YTD Actuals $’000 | Annual Revised Budget $’000 | % Spent to Annual Budget $’000s
Bridges | 460 | 540 | 85.1%
Buildings | 3,102 | 4,201 | 73.9%
Cemeteries | 132 | 138 | 96.0%
CWMS | 49 | 75 | 65.8%
Footpaths | 1,004 | 910 | 110.3%
Guardrails | - | - | 0.0%
Kerbing | 35 | 40 | 86.7%
Local Roads & Community Infrastructure Program (LRCIP) – phase 1 | 450 | 459 | 98.1%
Other - Retaining Walls, Street Furniture & Traffic Management | 470 | 561 | 83.7%
Roads | 7,888 | 8,049 | 98.0%
Sport & Recreation | 1,550 | 1,692 | 91.6%
Stormwater | 116 | 393 | 29.6%
Fleet | 1,917 | 2,227 | 86.1%
ICT | 791 | 1,035 | 76.4%
Plant & Equipment | 24 | 60 | 39.5%
Project Management Costs | - | 1,511 | 0.0%
 | 17,988 | 21,891 | 82.2%

## Slide 20
6. Savings Strategies
Administrative Savings Strategies | Status | Planned | Achieved
Remove media monitoring | Completed | $14,250 | $0
The service has been continued for another year and funding options are being considered |  |  | 
Stop taking cash payments | Completed | $9,500 | $9,500
Legal advice has highlighted complex challenges resulting in a pause on “ceasing cash payments”. However, savings have been achieved through implementation of other strategies in the library space resulting from the opening hours reduction. |  |  | 
Remove community arts project money from budget | Completed | $5,300 | $5,300
The budget item for community arts was no longer required and has been removed |  |  | 
Maintenance fees – contractors / materials | Completed | $5,000 | $5,000
Currently reviewing use of in-house staff for cemetery maintenance. Budget adjusted to accommodate. |  |  | 
Remove automatic CPI increase on contract and materials | Completed | $400,000 | $400,000
This has been fully implemented in the adopted budget and will be monitored through the year |  |  | 
Appliance replacement - all facilities | Completed | $10,000 | $10,000
Annual budget for appliance replacement reduced from $30k to $20k and will be monitored through the year |  |  | 
Cleaning contract - reduce frequency | Completed | $33,000 | $20,000
Negotiations on cleaning contract have resulted in $20k savings. No further cleaning savings will be possible. |  |  | 
Reduce no of multifunction devices | Completed | $12,000 | $12,000
Scoping commenced to reduce the number of devices from 18 down to 8. |  |  | 
Reduce public access computers | Completed | $10,000 | $10,000
Scoping commenced on renewal program to reduce number of computers and move to a ticketed/booking system for use of remaining computers. |  |  | 
Remove mobile data from laptops and tablets | Completed | $20,000 | $20,000
Mobile data services have been cancelled and staff advised of alternative Wi-Fi solutions if internet required outside of the office. |  |  | 
Reduce People & Culture budget allocation for legal fees | Completed | $15,000 | $15,000
Budget allocation was reduced and will be monitored throughout the year |  |  | 
Salary Savings | Completed | $200,000 | $200,000
Conduct workshops with clubs using internal resources | Completed | $5,000 | $5,000
Public Notification signage install and removal using internal resources | Completed | $20,000 | $14,518
The Savings Target was less than estimated due to an amendment to the Planning and Design Code that occurred, excluding signage requirements in the Productive Rural Landscape Zone. |  |  | 
Cease cadet engineer program | Completed | $12,000 | $12,000
Arboculture Consultancy | Completed | $5,000 | $5,000
Data management of utilities and scope 3 components | Completed | $16,000 | $0
 | TOTAL | $792,050 | $743,318
Chart: 
| Category 1
Series 1 | -962
Series 2 | 110
Column1
Target
$1,072k
Achieved $950k

## Slide 21
6. Savings Strategies
$xx Savings Achieved
Service and Revenue Changes | Status | Planned | Achieved
Tour Down Under - Limit commitment | Completed | $30,000 | $15,000
Budget savings realized were $15,000 due to event cost pressures |  |  | 
Remove funding to attract a major event to the hills | Completed | $20,000 | $20,000
Amend customer service operating hours from 8:30am to 9am | Completed | $12,500 | $12,500
Reduce/remove Adelaide Hills Tourism Funding | Completed | $7,500 | $7,500
New three-year funding agreement was approved and signed June 2023 with funding capped at the 2022-23 level |  |  | 
Reduce community grants | Completed | $10,000 | $10,000
Cease additional digital content offering | Completed | $20,000 | $20,000
No longer purchasing AHC specific digital library content as there is a large content range in SA library network |  |  | 
Digital online streaming/learning resources for language learning and online streaming | Completed | $8,000 | $8,000
Library CD collections - cease new purchases | Completed | $4,000 | $4,000
Printing and photocopying fee increase | On Track | $8,000 | $8,000
Reduce internal audit program from 4 to 3 audits annually | Completed | $15,000 | $15,000
Cease membership of Murray Darling Basin Association | Completed | $6,700 | $6,700
Increase non resident cemetery fees | Completed | $25,000 | $30,000
Increase outdoor dining permit fees | Completed | $7,000 | $7,000
Increase copyright application fee | Completed | $2,000 | $125
The volume of applications have been decreasing as compared to last financial year. This trend potentially due to economic climate impacting communities not needing to access their old house plans for renovations or sales, others chose not to proceed due to the fee. |  |  | 
Reduce community and recreation facilities grants | Completed | $20,000 | $20,000
Implement charge for food premises inspection for new businesses | Completed | $5,000 | $3,080
Standardise fee application for food premises inspection | Completed | $5,000 | $5,237
Cease bird monitoring on reserves following burning | Completed | $5,000 | $5,000
Cease vermin baiting in Stirling, Aldgate and Bridgewater | Completed | $10,000 | $10,000
Heathfield Resource Recovery Centre – Explore options for savings or cost recovery | Completed | $10,000 | $0
The Adelaide Hills Region Waste Management Authority are currently exploring options to reduce costs. No savings identified at this stage. |  |  | 
Waste education - not proceed with high intensity program | Completed | $50,000 | $50,000
Maintain waste education at current levels rather than increase the program as there has not been marked changes in diversion rates in recent years. |  |  | 
 | TOTAL | $280,700 | $207,142
Savings Strategies cont….

## Slide 22
7. Financial Performance
Overall Funding Statement as at 30 June 2024
Note: These figures are preliminary only. The fully reconciled figures will be presented to Council as part of the Budget Review report and Annual Financial Statements.

## Slide 23
MORE INFORMATION
63 Mt Barker Road
Stirling SA 5152
08 8408 0400
mail@ahc.sa.gov.au